## Monte Carlo
MONTE CARLO COST MODEL
5,000 iterations run live in-sheet. Edit the yellow input cells, then press F9 to re-roll. Stats below update automatically. | [7 empty] | ↓ SIMULATION ENGINE — one row per iteration (safe to ignore / collapse)
Item | Distribution | P1 | P2 | P3 | Central | SETTINGS |  | Labor | Materials | Equipment | Subcontractors | Permits & Fees | Risk Reserve | Total
Labor | pert | 40000 | 55000 | 90000 |  | Iterations | 5000
Materials | triangular | 30000 | 38000 | 60000 |  | Budget | 185000
Equipment | normal | 15000 | 3000 |  |  | Confidence | 80%
Subcontractors | uniform | 20000 | 35000
Permits & Fees | fixed | 5000
Risk Reserve | lognormal | 8000 | 4000
Base estimate
SUMMARY (live — press F9 to re-roll)
Mean (expected)
Std deviation
Minimum
Maximum
P10 (optimistic)
P50 (median)
P80 (conservative)
P90
P95
Recommended @ 80%
Contingency vs base
P(cost <= budget)

## Charts
DISTRIBUTION OF TOTAL COST
Bin # | Low | High | Center | Count
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
CUMULATIVE PROBABILITY (S-CURVE)
Cumulative % | Total cost
0%
5%
10%
15%
20%
25%
30%
35%
40%
45%
50%
55%
60%
65%
70%
75%
80%
85%
90%
95%
100%

## How to Use
MONTE CARLO COST MODEL — HOW IT WORKS
1. Go to the 'Monte Carlo' sheet.
Edit the YELLOW cells in the input table (P1/P2/P3) and the Budget/Confidence.
Each item samples from its distribution using the parameters you enter:
fixed P1 = value
uniform P1 = min, P2 = max
triangular P1 = min, P2 = most likely, P3 = max
pert P1 = min, P2 = most likely, P3 = max
normal P1 = mean, P2 = std dev
lognormal P1 = mean, P2 = std dev
2. Press F9 to re-roll all iterations. The SUMMARY and the charts update live.
(The model is volatile: it also re-rolls on any edit.)
3. Read the results:
Mean = expected total cost.
P80 = there is an 80% chance the real cost is at or below this.
Recommended @ confidence = the budget you should set to hit that confidence.
Contingency = recommended budget minus the deterministic base estimate.
P(cost <= budget) = probability you finish within the budget you entered.
4. To add or remove cost items, re-run generate_excel_model.py after editing
the ITEMS list at the top of the script (formulas are wired per item).
Note: uses NORM.INV / LOGNORM.INV / BETA.INV / PERCENTILE.INC / STDEV.S
→ requires Excel 2010 or newer (also works in LibreOffice Calc).