## Dashboard
MONTE CARLO COST MODEL
Currency | Years | Iterations | Confidence | Discount | Checks
▶ Run Simulation |  |  | 📅 Apply Years |  | ⬇ Export Report
Buttons need the VBA modules (vba/). Save as .xlsm. See vba/VBA_SETUP.md.
KEY OUTPUTS (filled by the macro)
Base Cost (ML) |  | Expected Cost |  | Expected Risk |  | Total Expected
P50 |  | P70 |  | P80 |  | P90
Contingency |  | Recommended Budget |  | NPV @ confidence |  | P95

## Setup
MODEL SETUP
Yellow cells are inputs. Run the simulation from the Dashboard (or Alt+F8 ▸ RunSimulation).
Project name | Sample Construction Project
Currency | SAR
Base year | 2025
Start year | 2025
Number of years | 5
Iterations | 10000
Confidence level | P80
Discount rate | 8%
VAT treatment | Excluded | ↳ inflation is per year on the Inflation sheet
Prepared by
Date
Confidence (numeric)

## Cost Lines
COST LINES — 3-Point Estimates (add rows freely; the macro reads them all)
➕ Add → AddCostLine |  |  | 🗑 Delete selected → DeleteCostLine
No. | Cost Item | Category | Description | Unit | Quantity | Min Unit Cost | Most Likely Unit Cost | Max Unit Cost | Min Total Cost | Most Likely Total Cost | Max Total Cost | Distribution | Include? | Notes
| Site Preparation | Civil | Site Preparation works | LS | 1 | 28000 | 38000 | 60000 |  |  |  | Triangular | Yes
| Foundations | Civil | Foundations works | LS | 1 | 45000 | 55000 | 75000 |  |  |  | Triangular | Yes
| Superstructure | Structural | Superstructure works | LS | 1 | 90000 | 120000 | 170000 |  |  |  | Pert | Yes
| MEP Systems | MEP | MEP Systems works | LS | 1 | 60000 | 80000 | 115000 |  |  |  | Pert | Yes
| Finishes | Architectural | Finishes works | LS | 1 | 30000 | 45000 | 70000 |  |  |  | Triangular | Yes
| Project Management | PM | Project Management works | LS | 1 | 20000 | 28000 | 40000 |  |  |  | Normal | Yes

## Cost Profiling
COST PROFILING — % per year (rows must total 100%)
No. | Cost Item | FY1 | FY2 | FY3 | FY4 | FY5 | FY6 | FY7 | FY8 | FY9 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | Total %
|  | 33.33% | 26.67% | 20% | 13.33% | 6.667% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | 33.33% | 26.67% | 20% | 13.33% | 6.667% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | 11.11% | 22.22% | 33.33% | 22.22% | 11.11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | 6.667% | 13.33% | 20% | 26.67% | 33.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | 6.667% | 13.33% | 20% | 26.67% | 33.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | 20% | 20% | 20% | 20% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%

## Risk Register
RISK REGISTER — probability-weighted 3PE impacts
➕ Add → AddRisk |  |  | 🗑 Delete selected → DeleteRisk
Risk ID | Risk Name | Category | Probability | Min Impact | Most Likely Impact | Max Impact | Distribution | Risk Owner | Include? | Notes
| Adverse ground conditions | Technical | 30% | 20000 | 45000 | 90000 | Triangular | Civil Lead | Yes
| Major design change | Commercial | 40% | 15000 | 30000 | 60000 | Pert | Design Mgr | Yes
| Material price spike | Market | 50% | 10000 | 25000 | 55000 | Triangular | Procurement | Yes
| Schedule delay | Delivery | 25% | 20000 | 40000 | 80000 | Pert | PM | Yes

## Risk Profiling
RISK PROFILING — % per year (rows must total 100%)
Risk ID | Risk Name | FY1 | FY2 | FY3 | FY4 | FY5 | FY6 | FY7 | FY8 | FY9 | FY10 | FY11 | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | FY23 | FY24 | FY25 | FY26 | FY27 | FY28 | FY29 | FY30 | Total %
|  | 33.33% | 26.67% | 20% | 13.33% | 6.667% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | 11.11% | 22.22% | 33.33% | 22.22% | 11.11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | 11.11% | 22.22% | 33.33% | 22.22% | 11.11% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
|  | 6.667% | 13.33% | 20% | 26.67% | 33.33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%

## Inflation
INFLATION — rate per year; cumulative factor compounds (FY1 = 1.0)
FY | Year | Inflation Rate | Cumulative Factor
FY1 |  | 0%
FY2 |  | 3%
FY3 |  | 3%
FY4 |  | 3%
FY5 |  | 3%
FY6 |  | 3%
FY7 |  | 3%
FY8 |  | 3%
FY9 |  | 3%
FY10 |  | 3%
FY11 |  | 3%
FY12 |  | 3%
FY13 |  | 3%
FY14 |  | 3%
FY15 |  | 3%
FY16 |  | 3%
FY17 |  | 3%
FY18 |  | 3%
FY19 |  | 3%
FY20 |  | 3%
FY21 |  | 3%
FY22 |  | 3%
FY23 |  | 3%
FY24 |  | 3%
FY25 |  | 3%
FY26 |  | 3%
FY27 |  | 3%
FY28 |  | 3%
FY29 |  | 3%
FY30 |  | 3%

## Results
RESULTS
▶ Run the simulation (Dashboard button or Alt+F8 ▸ RunSimulation) to populate these.
A. Total Cost Percentiles
Percentile | Total Cost
P10
P30
P50
P60
P70
P80
P90
P95
B. Contingency by Confidence
Confidence | Total Cost | Base Cost | Contingency | Contingency %
P50
P70
P80
P90
C. Annual Cash Flow by Confidence
Year | P50 | P70 | P80 | P90
D. NPV by Confidence
Confidence | Nominal Total | NPV
P50
P70
P80
P90

## Sensitivity
SENSITIVITY (TORNADO)
P90 − P10 spread of each driver's sampled value (filled by the macro).
Driver | Type | P10 | P90 | Range (P90−P10)

## Checks
MODEL CHECKS
Check | Result
Cost profile rows total 100%
Risk profile rows total 100%
Cost lines Min<=ML<=Max
Risks Min<=ML<=Max
Iterations > 0
Years between 1 and 30
Discount rate valid
All checks

## ChartData (hidden)
Center | Count | Cost | CumProb | Year | Cum P50 | Cum P80